## Start here
THE FDA GROUP
Annual Audit Program Planning Workbook
What this is
A working sheet for building next year's audit schedule. Fill in the Audit schedule tab, one row per audit. When it's done you have two things: a schedule we can price and resource, and a written record of how you decided what to audit.
The date that matters
Send us the schedule as soon as you can — ideally by October 1. Proposals and contracts begin in earnest during this time. November and December go to CV approvals, agendas, and travel booking. January audits run on whatever was decided in October.
How to use it
1. Delete the four sample rows (rows 3 to 6, shaded amber) on the Audit schedule tab.
2. Add one row per audit. Grey headers mark the fields we need to build a proposal; the rest we need to start booking.
3. Columns with dropdowns pull from the Lists tab. Edit those lists if your SOP uses different terms.
4. Send it over to us!
This workbook is a planning aid, not a regulatory requirement. Audit frequency and scope are determined by your own quality system and risk assessment procedures.

## Audit schedule
AUDIT | [6 empty] | SCHEDULING |  |  | SITE CONTACT | [6 empty] | QUALITY AGREEMENT |  | AUDITOR |  | OWNERSHIP
Site or supplier name | Location (city, country) | Audit type | Audit basis | Reason on the list | Duration (days) | Mode | Quarter | Fixed dates | Blackout windows | Contact name | Title | Phone | Email | Time zone | Working language | Interpreter needed | Agreement status | Notice period (days) | Previous auditor | Auditor decision | Coordination | Notes
Hovione FarmaCiencia SA | Loures, Portugal | GMP | Routine surveillance | Interval due | 2 | On-site | Q2 |  | August shutdown; Easter week Mar 26-29 | Ana Ferreira | QA Manager | +351 21 000 0000 | a.ferreira@example.com | WET (UTC+1) | English | No | In place, current | 30 | M. Alvarez | Retain | The FDA Group books | Third year with same auditor. Two open observations from 2026 to verify.
Suzhou BioPharma Co. Ltd | Suzhou, China | GMP | Qualification | New material or scope | 3 | On-site | Q3 |  | CNY late Jan-late Feb; Golden Week Oct 1-7 | Wei Lin | Head of Quality | +86 512 0000 0000 | w.lin@example.com | CST (UTC+8) | Mandarin | Yes | Not in place | 60 |  | Open | The FDA Group books | First commercial supply of API intermediate. Quality agreement in legal review.
Northlake Clinical Research | Raleigh, NC, USA | GCP | Routine surveillance | Quality event | 2 | On-site | Q1 | Feb 15-16 only |  | Dana Whitfield | Director, Clinical Ops | +1 919 555 0100 | d.whitfield@example.com | ET (UTC-5) | English | No | In place, current | 30 | J. Reyes | Retain | Our company books | Triggered by three protocol deviations in Q3 2026. Site can only host Feb 15-16.
Meridian Analytical Labs | Hyderabad, India | GLP | Routine surveillance | Interval due | 2 | Hybrid | Q2 |  | Fiscal year close Mar 31; Diwali (confirm date) | Priya Nair | QA Head | +91 40 0000 0000 | p.nair@example.com | IST (UTC+5:30) | English | No | In place, out of date | 45 | S. Kowalczyk | Rotate | Split | Last three audits produced thin findings. Rotating for fresh eyes. Agreement needs renewal.
Note on A3: SAMPLE ROWS. Rows 3 to 6 are examples showing the expected format. Delete all four before you start filling this in.

## Lists
Audit type | Audit basis | Reason on the list | Mode | Quarter | Interpreter needed | Quality agreement | Auditor decision | Coordination
GMP | Qualification | Interval due | On-site | Q1 | Yes | In place, current | Retain | Our company books
GCP | Routine surveillance | Quality event | Remote | Q2 | No | In place, out of date | Rotate | The FDA Group books
GLP | For-cause | Change at supplier | Hybrid | Q3 | TBD | Not in place | Open | Split
GCLP | Re-audit | New material or scope |  | Q4 |  | Unknown
CSV |  | Open CAPA
Pharmacovigilance (GVP) |  | Regulatory action
Quality system |  | Never audited
Supplier qualification
Edit these lists to match your own SOP terminology. The dropdowns on the Audit schedule tab follow them.